## Sheet2
Component | Test case ID | Test Senario | Description | Test steps | Test Data | Expected Result | Actual result | Status | Piriority | Severity | Screenshot
Register | TC-001 | User - Register with all valid details | Enter all required fields with valid data and name in arabic aphabet | 1- open the app 2- Press on "إنشاء حساب جديد" 3- Type all your data in the required fields 4- Press on "انشاء حساب" | name: مي كمال mobile: 01023205697 e-mail:maioiakamal96@gmail.com password:Abc123 rewrite password: Abc123 | a new account created With the same data that you entered | The account created Successfully | Pass |  |  | https://drive.google.com/file/d/1lamc7sXGc1He0P-Kmtaig01SAaEOS9gX/view?usp=drive_link
| TC-002 | User-Register with all valid details | Enter all required fields with valid data and name in English alphabet | 1- open the app 2- Press on "إنشاء حساب جديد" 3- Type all your data in the required fields 4- Press on "انشاء حساب" | name: mai kamal mobile: 01023205676 e-mail:maikamal346@gmail.com password:Conanran96# rewrite password: Conanran96# | a new account created With the same data that you entered | The account created Successfully | Pass |  |  | https://drive.google.com/file/d/1wrVoj1UBYiZAnY_zBv1xXYPFWjs3uj9O/view?usp=drive_link
| TC-003 | User-Register with phone number including country code | Verify that a user can successfully register using a phone number including a country code "+20" | 1- open the app 2- Press on "إنشاء حساب جديد" 3- Type all your data in the required fields 4- Press on "انشاء حساب" | name: mai kamal mobile: +201023205676 e-mail:maikamal346@gmail.com password:Conanran96# rewrite password: Conanran96# | a new account created With the same data that you entered | It mentioned incorrect phone number "ادخل رقم هاتف صحيح" | Fail | Medium | Low | https://drive.google.com/file/d/1D9ZR0pnKsGrZisHbrzRxKOkwIsMcS1YX/view?usp=drive_link
| TC-004 | User-Register with Empty phone number | Verify that user will not be able to register with empty phone number | 1- open the app 2- Press on "إنشاء حساب جديد" 3- Type all your data in the required fields except Phone number 4- Press on "انشاء حساب" | name: mai kamal mobile: e-mail:maikamal346@gmail.com password:Conanran96# rewrite password: Conanran96# | A user will receive an error message when try to register with empty phone number | It mentioned "ادخل رقم هاتف صحيح" | Pass |  |  | https://drive.google.com/file/d/1X-TF3WWecCKqzU7FfjJt2gYxh6B5qCFs/view?usp=drive_link
| TC-005 | User-Register with phone number including country code | Verify that a user can successfully register using a phone number including a country code "0020" | 1- open the app 2- Press on "إنشاء حساب جديد" 3- Type all your data in the required fields 4- Press on "انشاء حساب" | name: mai kamal mobile: 00201023205676 e-mail:maikamal346@gmail.com password:Conanran96# rewrite password: Conanran96# | a new account created With the same data that you entered | It mentioned incorrect phone number "ادخل رقم هاتف صحيح" | Fail | Medium | Low | https://drive.google.com/file/d/12ISzexkZTxdIeaIoTMR_G0I2sg8CEY_G/view?usp=drive_link
| TC-006 | User register with long Phone number | Verify that user can't register successfully when entering phone number with 13 digits | 1- open the app 2- Press on "إنشاء حساب جديد" 3- Type all your data in the required fields 4- Press on "انشاء حساب" | name: mai kamal mobile: 1234567892322 e-mail:maikamal346@gmail.com password:Conanran96# rewrite password: Conanran96# | A user will receive an error message when try to register with 13 digits phone number | It mentioned incorrect phone number "ادخل رقم هاتف صحيح" | Pass |  |  | https://drive.google.com/file/d/1l6VTJlW97lqEwhZY4Y_ei4hayLvD4umt/view?usp=drive_link
| TC-007 | User register with short Phone number | Verify that user can't register successfully when entering phone number with 3 digits | 1- open the app 2- Press on "إنشاء حساب جديد" 3- Type all your data in the required fields 4- Press on "انشاء حساب" | name: mai kamal mobile: 234 e-mail:maikamal346@gmail.com password:Conanran96# rewrite password: Conanran96# | A user will receive an error message when try to register with 3 digits phone number | It mentioned incorrect phone number "ادخل رقم هاتف صحيح" | Pass |  |  | https://drive.google.com/file/d/1dycASLZ4MY89iijhMVKDctR9e9yMnNQ7/view?usp=drive_link
| TC-008 | User register with phone number includes alphabets | Verify that user can't register successfully when entering alphabets in phone number field | 1- open the app 2- Press on "إنشاء حساب جديد" 3- Type all your data in the required fields 4- Press on "انشاء حساب" | name: mai kamal mobile: N01023205697 e-mail:maikamal346@gmail.com password:Conanran96# rewrite password: Conanran96# | A user should receive an error message when entering a phone number including alphabets | It mentioned incorrect phone number "ادخل رقم هاتف صحيح" | Pass |  |  | https://drive.google.com/file/d/1VuICW2cu1sXtgWq7wOramh8hyfvOxe7q/view?usp=drive_link
| TC-009 | User register with phone number includes space in the begining | Verify that user can't register successfully when entering a space at the begining | 1- open the app 2- Press on "إنشاء حساب جديد" 3- Type all your data in the required fields 4- Press on "انشاء حساب" | name: mai kamal mobile: 01023205697 e-mail:maikamal346@gmail.com password:Conanran96# rewrite password: Conanran96# | A user should receive an error message when entering a phone number including space | It mentioned incorrect phone number "ادخل رقم هاتف صحيح" | Pass |  |  | https://drive.google.com/file/d/1OzEcDgvWyG5rax1GxH_2e1QMho7GIqYx/view?usp=drive_link
| TC-010 | User-Register with empty E-mail | Verify that user can't register successfully when entering empty E-mail | 1- open the app 2- Press on "إنشاء حساب جديد" 3- Type all your data in the required fields 4- Press on "انشاء حساب" | name: mai kamal mobile: 01023205697 e-mail: password:Conanran96# rewrite password: Conanran96# | A user will receive an error message when try to register with empty E-mail field | It mentioned an error message below E-mail field "من فضلك ادخل بريد ألكتروني صحيح" | Pass |  |  | https://drive.google.com/file/d/1IV2mVQ87nIcxBEGdQROECeEhCV5Z4Kzx/view?usp=drive_link
| TC-011 | User-Register with incorrect E-mail | Verify that registeration will not be successfully done if the E-mail is incorrect | 1- open the app 2- Press on "إنشاء حساب جديد" 3- Type all your data in the required fields 4- Press on "انشاء حساب" | name: مي كمال mobile: 01023205697 e-mail: gmail.com password:Abc123 rewrite password: Abc123 | an error message should appear when entering a wrong E-mail | A red error message appears below E-mail field "من فضلك ادخل بريد ألكنروني صحيح" | Pass |  |  | https://drive.google.com/file/d/1Xu20xM_TG6HADhlw4W_LURwJJd2A_M8i/view?usp=drive_link
| TC-012 | User-Register wih no matching passwords | Verify that registeration will not be successfully done when user rewites a mismatched password | 1- open the app 2- Press on "إنشاء حساب جديد" 3- Type all your data in the required fields 4- Press on "انشاء حساب" | name: مي كمال mobile: 01023205697 e-mail: maioiakamal96@gmail.com password:Abc123 rewrite password: Abc1234 | An error message should appear below the rewitre password field | A red error message appears below تأكيد كلمه المرور "كلمة المرور غير متطابقة" | Pass |  |  | https://drive.google.com/file/d/1xOKx6MPBl3f5SQzAlI0tnZc6VSWpqYtf/view?usp=drive_link
| TC-013 | User-Register with no fields added | Verify that registeration will not be successfully done when user click on register with no fields added | 1- open the app 2- Press on "إنشاء حساب جديد" 3- Type no data in the required fields 4- Press on "انشاء حساب" | name: mobile: e-mail: password: rewrite password: | Error messages shoud appear below every empty required fields | Error messages appear below name, mobile, e-mail,password, rewrite password | Pass |  |  | https://drive.google.com/file/d/1b1kuHBpEusW3xtqmTm0HMtgN15n1DnMs/view?usp=drive_link
| TC-014 | User-Register with existing E-mail | Verify that registeration will not be successfully done if user registers with existing E-mail | 1- open the app 2- Press on "إنشاء حساب جديد" 3- Type all data in the required fields 4- Press on "انشاء حساب" | name: mai kamal mobile: 01023205697 e-mail:maikamal346@gmail.com password:Conanran96# rewrite password: Conanran96# | Error message should appear when register | Error message appears when you enter existing E-mail | Pass |  |  | https://drive.google.com/file/d/1Jy46chowXlcJ4G_2Al0rnzDvl0B6DZ9k/view?usp=drive_link
| TC-015 | User-Register redirecting to verification mail | Verify that user will be redirected to verification mail after entering registeration details | 1- open the app 2- Press on "إنشاء حساب جديد" 3- Type all data in the required fields 4- Press on "انشاء حساب" | name: mai kamal mobile: 01023205697 e-mail:maikamal346@gmail.com password:Conanran96# rewrite password: Conanran96# | User should be redirected to verification page after clicking on "تسجيل الدخول" | User registered directly with no verification page redirected | Fail | High | High | https://drive.google.com/file/d/1wrVoj1UBYiZAnY_zBv1xXYPFWjs3uj9O/view?usp=drive_link
| TC-016 | User-Register with existing details | Verify that registeration will not be successfully done if user enters existing details | 1- open the app 2- Press on "إنشاء حساب جديد" 3- Type all data in the required fields 4- Press on "انشاء حساب" | name: مي كمال mobile: 01023205697 e-mail:maioiakamal96@gmail.com password:Abc123 rewrite password: Abc123 | Error message should appear when register like user already exists | after you click on register it will get a validation error message | Pass |  |  | https://drive.google.com/file/d/1BmWC2jEM0cMZup5uKoob4myHr5OeKXah/view?usp=drive_link
| TC-017 | User-Register with empty password | Verify that registeration will not be successfully done if user enters empty password | 1- open the app 2- Press on "إنشاء حساب جديد" 3- Type all data in the required fields 4- Press on "انشاء حساب" | name: مي كمال mobile: 01023205697 e-mail:maioiakamal96@gmail.com password: rewrite password: | Error message should appear when register with empty password field | After you click on register it will get an error message below password field "هذا الحقل مطلوب" | Pass |  |  | https://drive.google.com/file/d/1NmreEN_8-1ixtI80G9lno6WJ0R2mUDuw/view?usp=drive_link
| TC-018 | User-Register password hide | Verifiy that the password will be hidden when the eye is closed and readable when eye is open | 1- open the app 2- Press on "إنشاء حساب جديد" 3- Type all data in the required fields 4- Press on "انشاء حساب" | Password: 123456 | User should be able to show password and hide password when clicking on the eye icon | when you click on the eye icon the password is hidden | Pass |  |  | https://drive.google.com/file/d/1N9HYBv9c3Pufn18OjKt40sz1T3ZUqyO4/view?usp=drive_link
| TC-019 | User-Register login page redirect | Verify that user can click on login page if he is aleady registered | 1- open the app 2- Navigate to "حسابي" 3- click on "تسجيل الدخول" | No data required | User should be able to redirect to login screen | User is redirected to login screen when he clicks on it | Pass
Login | TC-020 | User-Login | Enter all required fields with valid data | 1- open the app 2- Navigate to "حسابي" 3- Type all your data in the required fields 4- Press on "تسجيل الدخول" | E-mail: maioiakama96@gmail.com Password: Abc123 | A user can login to his existing account | User can login successfully | Pass |  |  | https://drive.google.com/file/d/15c6-mH-bk2MSwTpGPzisY6wXMQImQU5x/view?usp=drive_link
| TC-021 | User-Login with incorrect E-mail | Enter required data with valid password and invalid E-mail | 1- open the app 2- Navigate to "حسابي" 3- Type all your data in the required fields 4- Press on "تسجيل الدخول" | E-mail: gmail.com Password: Abc123 | An error message should appear with incorrect user or password | An error message appeared when entering incorrect E-mail | Pass |  |  | https://drive.google.com/file/d/11nlKV-IDT3uDTexF5VDVnNWgr11Mrh5d/view?usp=drive_link
| TC-022 | User Login with incorrect password | Enter required data with valid E-mail and invalid password | 1- open the app 2- Navigate to "حسابي" 3- Type all your data in the required fields 4- Press on "تسجيل الدخول" | E-mail:maioiakamal96@gmail.com Password:Abc1234 | An error message should appear with incorrect user or password | An error message appeared when entering incorrect Password | Pass |  |  | https://drive.google.com/file/d/1Cy5xXtzmPR6RnCwfI1rxBovPpyk1yXNh/view?usp=drive_link
| TC-023 | User Login with Facebook account | Verify that user can login through Facebook account | 1- open the app 2- Navigate to "حسابي" 3- Press on Facebook Icon | None as Facebook icon is missing in the application | Facebook icon should exists in the design clickable | Facebook icon is missing from the design | Fail | High | High | https://drive.google.com/file/d/1mUY5kxVA1g7eC-NnGFnEBow0b_KjNtPH/view?usp=drive_link
| TC-024 | User Login with Google+ account | Verify that user can login through Google+ account | 1- open the app 2- Navigate to "حسابي" 3- Press on Google+ Icon | None as Google+ Icon is not clickable | User should login through Google+ account | Google+ Icon is not clickable | Fail | High | High | https://drive.google.com/file/d/1mUY5kxVA1g7eC-NnGFnEBow0b_KjNtPH/view?usp=drive_link
| TC-025 | User Login with Apple account | Verify that user can login through Apple account | 1- open the app 2- Navigate to "حسابي" 3- Press on Apple Icon | None as Apple Icon is not clickable | User should login through Apple account | Apple Icon is not clickable | Fail | High | High | https://drive.google.com/file/d/1mUY5kxVA1g7eC-NnGFnEBow0b_KjNtPH/view?usp=drive_link
| TC-026 | User Login with no data | Verify that user will not be able to login if the fields are empty | 1- open the app 2- Navigate to "حسابي" 3- Press on "تسجيل الدخول" | No data to be added | User shouldn't be able to login with empty fields | Error message appears when you clicked on "تسجيل الدخول" | Pass |  |  | https://drive.google.com/file/d/1mfNitAM8e0u86xTHqgQtx0Icocj3E42o/view?usp=drive_link
| TC-027 | User Login with valid E-mail and empty password | Verify that user will not be able to login if the password field is empty | 1- open the app 2- Navigate to "حسابي" 3- Press on "تسجيل الدخول" | E-mail:maioiakamal96@gmail.com | User should receive an error message when entering empty password | A user receives an error message "validation errors" | Pass |  |  | https://drive.google.com/file/d/1EpWCCK0y7QKfP54PUguQzNQkpKAW-r5b/view?usp=drive_link
| TC-028 | User Login with empty E-mail and valid password | Verify that user will not be able to login if the E-mail field is empty | 1- open the app 2- Navigate to "حسابي" 3- Press on "تسجيل الدخول" | password:Abc123 | User should receive an error message when entering empty E-mail | A user receives an error message "validation errors" | Pass |  |  | https://drive.google.com/file/d/1RHWkQrFDCewkePwPwY6Sv0L1QM39QnI7/view?usp=drive_link
| TC-029 | Forget password page | Verify that user will be redirected to forget password page when clicking on it | 1- open the app 2- Navigate to "حسابي" 3- Press on "هل نسيت كلمه المرور" | No data required | User should be able to be redirected to forget password page | User redirected to forget password page successfully | Pass |  |  | https://drive.google.com/file/d/16KbjZAtjC_zJWjZ6Fr_CxStH7UbJAm56/view?usp=drive_link
| TC-030 | User Login user can paste the login fields | Verify that user can paste login details from outside the application | 1- open the app 2- Navigate to "حسابي" 3- Press on "تسجيل الدخول" | E-mail:maioiakamal96@gmail.com password:Abc123 paste the above from outside the app | User should be able to login by pasting the details from outside the application | User is able to login by pasting the details from outside the application | Pass |  |  | https://drive.google.com/file/d/1GxldfcwM8b1MwfsdI6alVX5uKAnoJngA/view?usp=drive_link
Forget password | TC-031 | Forget password | Verify that user can have verification code when forgeting password | 1- open the app 2- Navigate to "حسابي" 3- Press on "هل نسيت كلمه المرور" | Add verification mail maikamal346@gmail.com | User should be able to receive the verification code in E-mail | Verification code is not received in the E-mail | Fail | High | High | https://drive.google.com/file/d/1J7FCdRw_ynnlXadmIbK2HUUEBJIozMn1/view?usp=drive_link
| TC-032 | Forget password with incorrect E-mail | Verify that user can't receive a verification mail by adding incorrect E-mail | 1- open the app 2- Navigate to "حسابي" 3- Press on "هل نسيت كلمه المرور" | Add verification E-mail: gmail.com | User should receive error message when writing incorrect E-mail | Error message appears when entering wrong E-mail | Pass |  |  | https://drive.google.com/file/d/1XBGt7dDIwoy9GmCBpTXNnNK3W395aejo/view?usp=drive_link
| TC-033 | Forget password and entering wrong verification code | Verify that Error message will appear when entering wrong verification code | 1- open the app 2- Navigate to "حسابي" 3- Press on "هل نسيت كلمه المرور" | Add verification mail maikamal346@gmail.com | User should receive an error message when entering wrong verification code | Error message appears when entering wrong Verification code "error in verify code,please try again" | Pass |  |  | https://drive.google.com/file/d/1yHIDq0gFNV4Ybj1FO3Zu6ouewpfIwSlK/view?usp=drive_link
| TC-034 | Forget password- empty verification code | Verify that error message will appear when pressing "تسجيل الدخول" with no verification code entered | 1- open the app 2- Navigate to "حسابي" 3- Press on "هل نسيت كلمه المرور" 4- Press on Verify | Add verification mail maikamal346@gmail.com in verification code screen add nothing | User should receive an error message when pressing verify with no verification code | An error message appears when you press Verify without adding a verification code | Pass |  |  | https://drive.google.com/file/d/1wFUrrMt0zIh1c1nmHJpin3v51Xh2_HsP/view?usp=drive_link
| TC-035 | Forget password resend the code | Verify that user will receive the verification code when clicking on resend | 1- open the app 2- Navigate to "حسابي" 3- Press on "هل نسيت كلمه المرور" 4- Press on Verify 5- Press on resend the code | Add verification mail maikamal346@gmail.com in verification code screen click resend code | User should be able to receive the verification code in E-mail after clicking on resend password | Verification code is not received in the E-mail | Fail | High | High | https://drive.google.com/file/d/1u3_n0fMsznwAVVAeNT6WCLijlb-3JOxf/view?usp=drive_link